## Slide 1: Appendix 3: Refreshed WDES Action Plan 2022- 2024
Objective | Gap to address | Actions | Owner | Timescale
Improve staff sharing of disability/health condition at commencement of employment and during their career at CUH | WDES metric1 4.2% (498) staff recorded disability on ESR, compared with 20.5% (1,331) of staff survey respondents is low | Campaign to promote benefits of sharing disability status on ESR Senior Leaders role model and share their status on ESR Communication campaign - when and how to use My ESR for recording | Head of EDI Associate Director of Workforce Associate Director of Workforce | December 2022 December 2022 December 2022
Ensure staff with a disability LTC or illness have reasonable adjustments in place | WRES indicator 8: 75.9 % of CUH staff with a LTC or illness say that their employer has made adequate adjustment(s) to enable them to carry out their work | Fully launch, promote & embed the new centralised Workplace Adjustments Service that was launched in June 2022 and ensure this is well communicated. Launch campaign to promote Purple Passport | Occupational Health Head of EDI | December 2022 December 2022
Priority area : Reasonable adjustments 1/2

## Slide 2
Objective | Gap to address | Actions | Owner | Timescale
Ensure staff with a disability LTC or illness have reasonable adjustments in place (Cont) | WDES indicator 8: 75.9 % of CUH staff with a LTC or illness say that their employer has made adequate adjustment(s) to enable them to carry out their work | Accessibility of training: improve accessibility and adjustments for training and development opportunities Provide access to hearing loops and other relevant equipment LMS DOT booking registration schedules record adjustments needed for delegates | Learning and Development Head of DOT | March 2023 March 2023
Ensure workplace premises are accessible |  | Accessibility audit of premises commissioned and improvement action plan developed Signpost and provide support to disabled staff with applications for Blue Badge with briefing sessions | Estates and Facilities Estates and Facilities With Purple Network | March 2023 March 2023
Priority area : Reasonable adjustments 2/2

## Slide 3
Objective | Gap to address | Actions | Owner | Timescale
Improve recruitment of Disabled staff to CUH and reduce gap between Disabled and non-disabled staff | WDES metric 2 Non-disabled staff 1.1 times more likely to be appointed from shortlisting than Disabled staff Less likely to be in senior roles WDES Metric 5 52.6% of disabled staff who believe that their organisation provides equal opportunities for career progression or promotion | Review Recruitment processes and communications to include proactive offer of support and adjustments at interview, and importance of sharing personal characteristic information De-biasing the recruitment process, particularly through a disability and neurodiversity lens, to include a review of the information available on the Careers microsite and communications. | Head of Resourcing Head of Resourcing | March 2023 March 2023
Improve accessibility of training and development | Metric 5 above | Accessibility of training: improve accessibility and adjustments for training and development opportunities | Head of Learning and Development | March 2023
Priority area : Career progression

## Slide 4
Objective | Gap to address | Actions | Owner | Timescale
Rollout of new disability awareness training |  | Develop a disability awareness training proposal with a robust evaluation strategy including measures of performance and measures of effectiveness. Training to targeted at areas who would benefit most | Head of EDI team with Purple Network | March 2023
Review sickness and performance management processes | Metric 6 27.9% staff with LTC disability cp 19% non disabled, who have felt pressure from their manager to come to work, despite not feeling well enough to perform their duties | Review sickness Management process including implementation of NHS Employers guidance on Disability leave Review performance management processes and undertake Equality Impact Assessment | Interim Head of Employee relations with Purple Network Interim Head of Employee relations with Purple Network | March 2023 March 2023
Priority area: Creating a supportive inclusive culture

## Slide 5
Objective | Gap to address | Actions | Owner | Timescale
Support Purple Network to thrive | All WDES metrics Metric 9a Staff engagement score Disabled staff is 6.6 which is lower then non-disabled staff 7.1 Trust Staff engagement score is 7 (0-10) | Celebrate Disability History month Support Purple network, Open Mind Network and Neurodiversity staff group to thrive and be a voice for disabled staff, to shape WDES action plan and involved in decision making. Refresh committee role descriptions and terms of reference Implement time off arrangements facilities for network chairs and secretaries Introduce Honorarium for network co-chairs Embed governance arrangements of staff network | The Purple Network Head of EDI team with Purple Network Head of EDI team with Purple Network Head of EDI team with Purple Network Head of EDI team with Purple Network | December- annually Ongoing September 2022 March 2023 September 2022
Priority area: Creating a supportive inclusive culture